## Weekly Scorecard
Weekly Leadership Scorecard — Roofing OPS
10 KPIs reviewed every Monday at 8am. Red = miss. Yellow = within 10% of target. Green = on/above target.
# | KPI | Owner | Target | Direction | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
1 | Revenue ($K) | Owner | 100 | Higher | 95 | 102 | 88 | 110 | 118 | 92 | 78 | 65 | 82 | 105 | 115 | 122 | 118
2 | New deals signed | Sales mgr | 8 | Higher | 7 | 9 | 6 | 10 | 11 | 8 | 5 | 4 | 7 | 9 | 10 | 12 | 11
3 | Close rate % | Sales mgr | 45 | Higher | 42 | 44 | 38 | 46 | 48 | 41 | 35 | 32 | 40 | 43 | 45 | 47 | 46
4 | Avg GM % (closed jobs) | Owner | 42 | Higher | 43 | 42 | 40 | 43 | 41 | 40 | 39 | 38 | 40 | 41 | 42 | 43 | 42
5 | Jobs completed | Production | 7 | Higher | 6 | 8 | 7 | 8 | 9 | 7 | 6 | 5 | 6 | 8 | 9 | 10 | 9
6 | Callbacks (count) | Production | 0 | Lower | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 0
7 | AR > 60 days ($K) | Office mgr | 25 | Lower | 22 | 26 | 32 | 38 | 42 | 38 | 35 | 28 | 24 | 22 | 20 | 18 | 20
8 | Cash on hand ($K) | Owner | 100 | Higher | 142 | 148 | 132 | 118 | 102 | 88 | 78 | 92 | 112 | 128 | 148 | 165 | 172
9 | Owner hours/week | Owner | 45 | Lower | 62 | 64 | 58 | 56 | 60 | 58 | 52 | 48 | 50 | 48 | 46 | 44 | 42
10 | L10 attendance rate | Owner | 100 | Higher | 100 | 100 | 80 | 100 | 100 | 100 | 100 | 80 | 100 | 100 | 100 | 100 | 100

## Rocks (Q Priorities)
Quarterly Rocks
Top 3–7 priorities for the quarter. One owner per rock. Reviewed at L10.
# | Rock | Owner | Due Date | Status | % Complete | Notes
1 | Implement job costing in ServiceTitan + train office mgr | Owner | 2026-06-30 | On Track | 65% | Phase 1 complete; training scheduled wk of 6/9.
2 | Hire production manager (filter, interview, ramp) | Owner | 2026-07-15 | Off Track | 30% | 2 candidates dropped. Reopen sourcing 5/26.
3 | Build weekly KPI dashboard (live) | Office mgr | 2026-06-15 | On Track | 80% | Sheet live; needs ServiceTitan API tie-in.
4 | Document top 5 SOPs (dispatch, closeout, AR) | Office mgr | 2026-07-31 | On Track | 40% | Dispatch SOP drafted; closeout in progress.
5 | Tighten AR — automated 30/45/60-day collections | Office mgr | 2026-06-30 | At Risk | 45% | Automation built; needs final QBO sync test.

## Issues List (IDS)
Issues List — Identify, Discuss, Solve
Drop anything that's getting in the way. Owner + due date when solved.
# | Date raised | Raised by | Issue | Discussion | Solve / Action | Owner | Due
1 | 2026-05-12 | Production lead | Sub-2 left 2 jobs short on cleanup | Repeated complaints from Storm jobs | Issue formal warning + tie cleanup to final pay | Owner | 2026-05-26
2 | 2026-05-12 | Office mgr | QBO not auto-syncing supplier 1 invoices | Manual entry adding 2hrs/wk | Reconnect ABC Supply integration; test | Office mgr | 2026-05-23
3 | 2026-05-19 | Sales mgr | Tom's close rate at 22% | Below 35% floor for 3 weeks | Ride-along + retrain on objection handling | Sales mgr | 2026-06-02
4 | 2026-05-19 | Owner | No backup for office mgr if she's out | Single point of failure on AR + dispatch | Document SOPs + cross-train asst by 7/15 | Office mgr | 2026-07-15

## To-Do Tracker
Weekly To-Dos
7-day commitments from L10. Anything not done by next L10 becomes an Issue.
# | Created | Owner | Action | Due | Done?
1 | 2026-05-19 | Owner | Call Sub-2 GM about cleanup issue | 2026-05-22 | Yes
2 | 2026-05-19 | Office mgr | Reset ABC Supply QBO integration | 2026-05-23 | Yes
3 | 2026-05-19 | Sales mgr | Ride-along with Tom on Tues + Wed | 2026-05-27 | In Progress
4 | 2026-05-19 | Office mgr | Draft closeout SOP v1 | 2026-05-30 | No
5 | 2026-05-19 | Owner | Re-engage production mgr candidates | 2026-05-26 | Yes